## Sheet1
Risk Matrix
|  | Negligible | Minor | Major | Hazardous | Catastrophic
| Very Unlikely | Low | Low | Low medium | Medium | Medium
| Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
| Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
| Likely | Low | Low medium | Medium | Medium high | High
| Very Likely | Low medium | Medium | Medium high | High | High
Final Project Risk Assessment
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
Losing work | Losing work will affect project succes | Frequently saving work | Saving on multiple places | Very Unlikely | Minor | Low
Sickness | Being sick will make it difficult to finish as extra pressure is put on the rest of the team | Keeping healthy habits and taking regular breaks | Being cautious about my health | Moderate | Major | Medium
PC damage | If someone's PC breaks down, risks lost work and may not be able to contribute | Checking computer health | Monitoring PC health | Unlikely | Hazardous | Medium
No database conncetion | Without the db connection, app will not work properly | testing the connection after each build | Regularly testing the connection ensuring correct data are passed | Moderate | Major | Medium
No internet | No access to GitHub | Ensuring reliable ISP provider | Stable signal with alternative connection available | Unlikely | Catastrophic | Medium High
Project app does not compile | Project not compiling will mean failure of the project deliverables | Complete syntax checks and unit tests | Frequently checking syntax and completing unit tests | Likely | Catastrophic | High